## Orifice Plate VDRL
Vendor Document Requirement List (VDRL) — Orifice Plate (ISO 5167-2 / ASME MFC-3M) — InstruNexus
Seq | Deliverable | Category | Applicability | Standard/Notes | Submission Purpose (R/W/F) | Required? | Required along with Bid | To Submit after PO | Part of MRB | Vendor Document No. | First Submittal Due (wks from PO) | Revision | Submission Date | Client Action (A/Revise/Comment) | Final Status | Remarks
1 | Supplier Document Register/List (SDRL) | Project Admin & Planning | All |  | R | Yes | No | Yes | No
2 | Project Quality Plan (PQP) / Quality Management Plan | Project Admin & Planning | All | Align with ISO 9001 supplier QMS | R | Yes | No | Yes | Yes
3 | Inspection & Test Plan (ITP) with hold/witness points | Project Admin & Planning | All | Include metrology methods for dimensional checks | R/W | Yes | If requested | Yes | Yes
4 | Manufacturing / Fabrication Schedule | Project Admin & Planning | All | Milestones and planned submittal dates | R | Yes | No | Yes | No
5 | NCR / Deviation / Concession & Corrective Action templates | Project Admin & Planning | All |  | R | Yes | No | Yes | No
6 | Orifice Plate Data Sheet (per tag) | Design & Engineering | All | Include size, Sch., fluid, β, ΔP, taps, plate type, material | R | Yes | If requested | Yes | Yes
7 | Sizing & Uncertainty Calculations | Design & Engineering | All | Per ISO 5167-2 / ASME MFC-3M; show Re range, expansibility, Cd basis | R | Yes | If requested | Yes | Yes
8 | General Arrangement (GA) drawing — orifice plate | Design & Engineering | All | Outline, handle/marking, flow direction, tap locations, tagging | R | Yes | If requested | Yes | Yes
9 | Manufacturing / Detail drawing with tolerances | Design & Engineering | All | Bore size, edge geometry, bevel, surface finish, flatness, concentricity | R | Yes | No | Yes | Yes
10 | Marking & Traceability Plan | Design & Engineering | All | Heat no., tag, β, bore, standard, flow arrow | R | Yes | No | Yes | Yes
11 | Primary Element GA — meter run / orifice fitting (if in scope) | Design & Engineering | If meter run/fitting supplied | Tap locations, straight runs, connections, supports | R | If applicable | If requested | If applicable | Yes
12 | Material Control & Traceability Procedure | Procedures & QC | All |  | R | Yes | No | Yes | Yes
13 | Dimensional Inspection Procedure | Procedures & QC | All | Acceptance criteria aligned to ISO 5167-2 | R | Yes | No | Yes | Yes
14 | Surface Finish / Edge Inspection Procedure | Procedures & QC | All | Edge radius/finish checks; gauge/microscope method | R | Yes | No | Yes | Yes
15 | Positive Material Identification (PMI) Procedure | Procedures & QC | If alloy grade control required |  | R | If applicable | No | If applicable | Yes
16 | Welding Procedures (WPS/PQR/WPQR) | Procedures & QC | If welded tappings/spools/fittings |  | R | If applicable | No | If applicable | Yes
17 | NDE Procedures (VT/PT/RT/MT as applicable) | Procedures & QC | If welds present |  | R | If applicable | No | If applicable | Yes
18 | Pressure Test Procedure | Procedures & QC | If meter run/fitting supplied | Hydro/pneumatic test medium, pressure, duration, acceptance | R/W | If applicable | No | If applicable | Yes
19 | Cleaning, Passivation & Preservation/Packing Procedures | Procedures & QC | All |  | R | Yes | No | Yes | Yes
20 | Coating/Painting Procedure & Data Sheets | Procedures & QC | If CS carriers/fittings/spools | Surface prep, DFT, cure schedule | R | If applicable | No | If applicable | Yes
21 | Calibration/Verification Plan for Inspection Tools | Procedures & QC | All | Traceable to ISO/IEC 17025 | R | Yes | No | Yes | Yes
22 | Mill Test Certificates (EN 10204 3.1 / 3.2) | Materials & Compliance | All wetted materials | Plates, carrier rings, fittings, fasteners | F | Yes | No | Yes | Yes
23 | NACE MR0175 / ISO 15156 Compliance Statement | Materials & Compliance | If sour service specified |  | F | If applicable | If applicable | If applicable | Yes
24 | REACH/ROHS or Regional Material Compliance | Materials & Compliance | If contract requires |  | F | If applicable | If applicable | If applicable | Yes
25 | Heat Treatment Records | Materials & Compliance | If any heat-treatment performed |  | F | If applicable | No | If applicable | Yes
26 | Raw Material Receiving Inspection Report | Inspection Records | All | Visual, grade, heat no. verification | F/W | Yes | No | Yes | Yes
27 | Dimensional Inspection Report — orifice plate | Inspection Records | All | OD/ID, thickness, bore size, concentricity, flatness, edge geometry, surface finish | F | Yes | No | Yes | Yes
28 | Marking/Stamps Verification Report | Inspection Records | All | β, tag, flow arrow, standard, bore | F | Yes | No | Yes | Yes
29 | PMI Reports | Inspection Records | If specified |  | F | If applicable | No | If applicable | Yes
30 | Hardness Test Report | Inspection Records | If specified by service |  | F | If applicable | No | If applicable | Yes
31 | NDE Reports for Welds (VT/PT/RT/MT) | Inspection Records | If welded items present |  | F | If applicable | No | If applicable | Yes
32 | Calibration Certificates — gauges & instruments | Inspection Records | All | Traceable to ISO/IEC 17025 | F | Yes | No | Yes | Yes
33 | Final Inspection & Release Report (per ITP) | Inspection Records | All |  | F/W | Yes | No | Yes | Yes
34 | Hydrostatic/Pressure Test Certificate | Pressure Integrity | If meter run/fitting supplied | Charts, pressure, duration, acceptance | F/W | If applicable | No | If applicable | Yes
35 | Leak Test Report | Pressure Integrity | If specified | Pneumatic/helium leak tests | F | If applicable | No | If applicable | Yes
36 | Valve/Manifold Test Reports | Pressure Integrity | If valves/manifolds included |  | F | If applicable | No | If applicable | Yes
37 | Surface Preparation Report (profile checks) | Coating & Packing | If coated items supplied |  | F | If applicable | No | If applicable | Yes
38 | Dry Film Thickness (DFT) & Holiday Test Reports | Coating & Packing | If coated items supplied |  | F | If applicable | No | If applicable | Yes
39 | Preservation & Packing Records with Photos | Coating & Packing | All | Crating, humidity indicators if specified | F | Yes | No | Yes | Yes
40 | Storage & Handling Instructions | Coating & Packing | All |  | F | Yes | No | Yes | Yes
41 | Certificate of Conformity/Compliance (CoC) | Certification & Conformity | All | To PO, datasheet, ISO 5167-2 / ASME MFC-3M | F | Yes | No | Yes | Yes
42 | ATEX/PED Statements | Certification & Conformity | Only if project requires |  | F | If applicable | If applicable | If applicable | Yes
43 | Installation, Operation & Maintenance (IOM) | Manuals & Installation | All | Orientation, gaskets, tightening, storage | F | Yes | No | Yes | Yes
44 | Straight-Length/Flow Conditioner Requirements | Manuals & Installation | If meter run supplied | Upstream/downstream lengths per ISO 5167-2 | F | If applicable | No | If applicable | Yes
45 | Torque Recommendations for Bolting | Manuals & Installation | If bolting supplied |  | F | If applicable | No | If applicable | Yes
46 | Site Receiving & Installation Checklist | Manuals & Installation | All |  | F | Yes | No | Yes | Yes
47 | As-built GA & Detail Drawings | As-built & Close-out | All | Final dimensions and tolerances | F | Yes | No | Yes | Yes
48 | Final Data Book / Manufacturer’s Record Book (MRB) | As-built & Close-out | All | Indexed PDF + native files where applicable | F | Yes | No | Yes | Yes
49 | Packing List & Shipping Release; Country of Origin (if required) | As-built & Close-out | All |  | F | Yes | No | Yes | Yes
50 | Spare Plate List & Recommended Spares | As-built & Close-out | If spares in scope | Include storage instructions | F | If applicable | No | If applicable | Yes

## Legend & Instructions
VDRL Legend & Instructions — Orifice Plate
New Columns:
- Required along with Bid: Mark 'Yes' items expected in the technical offer. Use 'If requested' when your RFQ explicitly asks. Use 'If applicable' for conditional items (e.g., ATEX/NACE).
- To Submit after PO: Default 'Yes' for all required items; 'If applicable' when scope/service dictates.
- Part of MRB: Items to be included in the final Manufacturer’s Record Book.
Stage Codes: R = For Review; W = Client Witness per ITP; F = For Records at final handover.
Standards: ISO 5167-2, ASME MFC-3M, EN 10204 (MTC), NACE MR0175/ISO 15156 (sour), ISO/IEC 17025 (calibration).
Suggested due dates from PO: SDRL/PQP/ITP — 2 weeks; Drawings & calcs — 3–4 weeks; Final records — before shipment.