## Rotameter VDR
Vendor Document Requirement (VDR) — Rotameter (Variable Area Flowmeter) — InstruNexus
Seq | Deliverable | Category | Applicability | Standard/Notes | Submission Purpose (R/W/F) | Required? | Required along with Bid | To Submit after PO | Part of MRB | Vendor Document No. | First Submittal Due (wks from PO) | Revision | Submission Date | Client Action (A/Revise/Comment) | Final Status | Remarks
1 | Supplier Document Register/List (SDRL) | Project Admin & Planning | All |  | R | Yes | No | Yes | No
2 | Project Quality Plan (PQP) / Quality Management Plan | Project Admin & Planning | All | Align with ISO 9001 supplier QMS | R | Yes | No | Yes | Yes
3 | Inspection & Test Plan (ITP) incl. witness points | Project Admin & Planning | All | Include calibration/verification, leak tests (if pressurized body), functional checks (if with transmitter) | R/W | Yes | If requested | Yes | Yes
4 | Manufacturing / Assembly Schedule | Project Admin & Planning | All | Milestones and submission plan | R | Yes | No | Yes | No
5 | Nonconformance/Concession/Deviation & Corrective Action templates | Project Admin & Planning | All |  | R | Yes | No | Yes | No
6 | Instrument Datasheet — Rotameter (per tag) | Design & Engineering | All | Tube type (glass/metal), size/rating, end connection, flow range & units, scale type, fluid properties, min/max P/T | R | Yes | Yes | Yes | Yes
7 | Application & Sizing Check | Design & Engineering | All | Density/viscosity basis, range selection, expected turndown, pressure drop, gas compressibility corrections | R | Yes | Yes | Yes | Yes
8 | Accuracy & Performance Statement | Design & Engineering | All | Reference accuracy, linearity, repeatability, scale readability, temperature/pressure effects | R | Yes | Yes | Yes | Yes
9 | General Arrangement (GA) — Meter Body | Design & Engineering | All | Face-to-face/length, connections, materials, rating, mounting orientation, purge or bypass details | R | Yes | Yes | Yes | Yes
10 | Float/Guide/Restriction Details & Materials | Design & Engineering | All | Float geometry/material (SS, Hastelloy, PTFE), guide type, stops, springs (if any) | R | Yes | Yes | Yes | Yes
11 | Scale Artwork / Dial Layout | Design & Engineering | All | Units, range, custom marking, dual scales, reference conditions | R | Yes | Yes | Yes | Yes
12 | Transmitter/Alarm Option (if provided) — GA & Wiring | Design & Engineering | If with 4–20 mA/HART or switches | Terminals, entry sizes, enclosure rating, setpoint adjustment range | R | If applicable | If applicable | If applicable | Yes
13 | Materials of Construction List (wetted & non-wetted) | Design & Engineering | All | Tube (glass/metal), float, body, seals/elastomers, bolts, indicator housing | R | Yes | Yes | Yes | Yes
14 | Pressure/Temperature Derating Curves (body/tube) | Design & Engineering | All | Allowable service envelope incl. glass protection cover (if any) | R | Yes | Yes | Yes | Yes
15 | Compliance Matrix to Project Specs / Datasheet | Design & Engineering | All | Point-by-point compliance; list deviations | R | Yes | Yes | Yes | Yes
16 | Calibration/Verification Procedure | Procedures & QC | All | ISO/IEC 17025 traceability; points across scale; reference medium/conditions; correction method for gas/liquid | R | Yes | If applicable | Yes | Yes
17 | Functional Test Procedure (if transmitter/switch) | Procedures & QC | If electronics supplied | Output scaling, setpoint/alarm checks, fail-safe behavior | R | If applicable | If applicable | If applicable | Yes
18 | Leak/Pressure Test Procedure — pressure containing parts | Procedures & QC | Metal tube/pressurized housings | Test pressure, duration, acceptance criteria | R/W | If applicable | If applicable | If applicable | Yes
19 | Cleaning, Preservation & Packing Procedure | Procedures & QC | All | Protection sleeves/caps, glass protection, humidity/shock indicators if specified | R | Yes | No | Yes | Yes
20 | Software/Firmware Handling & Cybersecurity Guide | Procedures & QC | If smart transmitter | Default passwords, write lock, security switch | R | If applicable | No | If applicable | Yes
21 | Hazardous Area Certificates (ATEX/IECEx) + Schedules | Compliance & Certifications | If Ex electronics | Entity parameters, temp class, EPL/Zone, installation conditions | R/F | If applicable | If applicable | If applicable | Yes
22 | EMC/EMI Compliance Statement | Compliance & Certifications | If electronics | IEC 61326 series or equivalent | F | If applicable | If applicable | If applicable | Yes
23 | Electrical Safety (IEC 61010-1) Declaration | Compliance & Certifications | If electronics | Safety of electrical equipment | F | If applicable | If applicable | If applicable | Yes
24 | Ingress Protection (IP66/67) Compliance Statement | Compliance & Certifications | If enclosure/HMI | IEC 60529 | F | If applicable | If applicable | If applicable | Yes
25 | PED/UKCA/CE Declaration (as applicable) | Compliance & Certifications | Jurisdiction dependent | Category/Module or SEP (as applicable) | F | If applicable | If applicable | If applicable | Yes
26 | NACE MR0175/ISO 15156 Compliance (wetted metallics) | Compliance & Certifications | If sour service | Body/float/trim (wetted) | F | If applicable | If applicable | If applicable | Yes
27 | RoHS/REACH or regional material compliance | Compliance & Certifications | If contract requires |  | F | If applicable | If applicable | If applicable | Yes
28 | 3-A/EHEDG Hygienic Approval | Compliance & Certifications | Sanitary service | Hygienic design certificate/schedule | F | If applicable | If applicable | If applicable | Yes
29 | Mill Test Certificates (EN 10204 3.1) — wetted metallics | Materials & Special Service | Metal tube/body | Body, wetted fittings, fasteners | F | If applicable | If applicable | If applicable | Yes
30 | Certificate of Analysis / CoC — Glass Tube | Materials & Special Service | Glass tube rotameters | Borosilicate (or specified) grade, batch traceability | F | If applicable | If applicable | If applicable | Yes
31 | Elastomer/Polymer Compliance (FDA/WRAS if required) | Materials & Special Service | If specified | O-rings/gaskets approvals | F | If applicable | If applicable | If applicable | Yes
32 | Calibration/Verification Certificate (as-left) | Inspection & Test Records | All | Reference medium/conditions; points across scale; expanded uncertainty; correction curves if applicable | F/W | Yes | No | Yes | Yes
33 | Functional Test Report (if transmitter/switch) | Inspection & Test Records | If electronics supplied | Outputs, alarm setpoint verification, fail-safe action | F | If applicable | No | If applicable | Yes
34 | Leak/Pressure Test Certificate — pressure containing parts | Inspection & Test Records | Metal tube/pressurized housings | Pressure, duration, acceptance | F/W | If applicable | No | If applicable | Yes
35 | Glass Tube Visual/Integrity Inspection Record | Inspection & Test Records | Glass tube rotameters | Visual defects, seating, protection cover, pressure rating label check | F | If applicable | No | If applicable | Yes
36 | Gauge & Calibrator Certificates used for tests | Inspection & Test Records | All | Traceability chain with due dates | F | Yes | No | Yes | Yes
37 | EDD/DTM/Device Files & Version List | Software & Integration | If smart transmitter | Provide files and version compatibility matrix | F | If applicable | If applicable | If applicable | Yes
38 | GSD/EDS files (Profibus PA/FF) | Software & Integration | If FF/PA used | Node defaults, function blocks | F | If applicable | If applicable | If applicable | Yes
39 | Communication Conformance Certificate (HART/FF/PA) | Software & Integration | If digital comms device | FieldComm Group/PI conformance | R/F | If applicable | If applicable | If applicable | Yes
40 | Host System Integration Notes | Software & Integration | If electronics | DCS/AMS/PRM/800xA/FDM compatibility and parameters | F | If applicable | If applicable | If applicable | Yes
41 | Installation, Operation & Maintenance (IOM) Manual | Manuals & Installation | All | Orientation (vertical/horizontal), straight-run guidance, purge connections, glass handling cautions | F | Yes | If requested | Yes | Yes
42 | Mounting/Bracket Drawings & Torque Values | Manuals & Installation | All | Bolting/torque, gasket guidance, panel mounting (purge types) | F | Yes | If requested | Yes | Yes
43 | Storage & Handling Instructions | Manuals & Installation | All | Caps, humidity/temp storage, glass protection, transport packaging | F | Yes | No | Yes | Yes
44 | As-built Configuration & Parameter List (per tag) | As-built & Close-out | If electronics | Range, units, outputs, alarm setpoints, damping/filters, comm address | F | If applicable | If applicable | If applicable | Yes
45 | Serial Number-to-Tag Cross-Reference List | As-built & Close-out | All | Include model code and, if applicable, firmware version | F | Yes | No | Yes | Yes
46 | Final Data Book / Manufacturer’s Record Book (MRB) | As-built & Close-out | All | Indexed PDF with bookmarks + native files as applicable | F | Yes | No | Yes | Yes
47 | Packing List & Country of Origin (if required) | As-built & Close-out | All |  | F | Yes | No | Yes | Yes
48 | Preservation & Packing Records with Photos | Packing & Logistics | All | Transit shock/humidity indicators if specified | F | Yes | No | Yes | Yes
49 | Shipping, Handling & Lifting Instructions | Packing & Logistics | All | Orientation, lifting points, glass protection, flange protectors | F | Yes | No | Yes | Yes

## Legend & Instructions
Legend & Instructions — Rotameter (Variable Area) VDR
How to Use
1) Vendor to submit all items marked 'Required? = Yes'. Items marked 'If applicable' apply when the service/scope requires (e.g., Ex electronics, sour service, sanitary).
2) R/W/F codes: R = For Review/Approval prior to manufacture; W = Hold/Witness point per ITP; F = For Records at final handover.
3) Typical bid-stage inclusions: Datasheet, Application/sizing check, Accuracy statement, GA and materials list, Scale artwork, Derating curves, Compliance matrix.
4) Standards reference (typical): ISO/IEC 17025 (calibration), IEC 61326 (EMC), IEC 61010-1 (safety), IEC 60529 (IP), EN 10204 (MTC), NACE MR0175/ISO 15156 (sour), 3-A/EHEDG (hygienic, if applicable).
5) Suggested due dates from PO: SDRL/PQP/ITP — 2 weeks; Drawings/config docs — 3–4 weeks; Final records — prior to shipment.
6) MRB content should include: calibration/verification certificate, test records, conformance certificates, materials certificates (metal/glass CoA as applicable), manuals, as-built configuration, and packing list.