## Continuous Emissions
CEMS Analyzer Commissioning Checklist
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | Continuous Emissions Monitoring System
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Pre-Requisites | Verify pre-commissioning checklist signed off
Pre-Requisites | Confirm datasheet, calibration, and regulatory compliance certificates
Pre-Requisites | Check calibration gas cylinders available and valid
Pre-Requisites | Verify sample system installed per GA drawings
Power-Up / Energization | Energize analyzer cabinet
Power-Up / Energization | Check power supply redundancy
Power-Up / Energization | Verify UPS switchover
Power-Up / Energization | Confirm comms with DCS
Functional Testing | Perform zero calibration with N2
Functional Testing | Perform span calibration with certified gases
Functional Testing | Verify automatic calibration cycle operation
Functional Testing | Check drift limits compliance with regulations
Functional Testing | Verify alarm setpoints for gas limits
Functional Testing | Confirm analyzer response time
Integration & Interlocks | Verify emissions signals in DCS
Integration & Interlocks | Check historian logging for regulatory compliance
Integration & Interlocks | Confirm alarms/events recorded
Integration & Interlocks | Check Cause & Effect shutdowns tested
Safety & Compliance | Verify hazardous area compliance
Safety & Compliance | Confirm calibration gas cert traceability
Safety & Compliance | Close punch items
© Instrunexus ¦ www.instrunexus.com