## Continuous Emissions
Pre‑Commissioning Checklist – CEMS
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | Continuous Emissions Monitoring System
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Documentation Verification | Verify tag vs. P&ID and instrument index
Documentation Verification | Check datasheet vs. installed system
Documentation Verification | Review calibration/test certificates
Documentation Verification | Confirm CEMS meets regulatory requirements
Documentation Verification | Verify vendor GA drawings
Sampling System | Inspect sampling probe condition
Sampling System | Check probe heater operation
Sampling System | Verify sample line insulation/heat tracing
Sampling System | Inspect sample filter condition
Sampling System | Check condensate drain system
Sampling System | Confirm sample flow rate
Gas Conditioning | Verify chiller operation
Gas Conditioning | Check moisture removal efficiency
Gas Conditioning | Inspect filter replacement records
Gas Conditioning | Check bypass/vent lines operable
Gas Conditioning | Confirm calibration gas ports installed
Analyzer Installation | Check analyzer rack/cabinet mounting
Analyzer Installation | Verify power supply connections
Analyzer Installation | Check air purge system operation
Analyzer Installation | Confirm accessibility for maintenance
Analyzer Installation | Verify environmental conditions
Electrical/Communication | Check wiring vs. diagram
Electrical/Communication | Verify grounding/shielding
Electrical/Communication | Inspect junction box tagging
Electrical/Communication | Check communication signals to DCS
Electrical/Communication | Verify UPS supply backup
Calibration & Functional | Perform zero/span calibration with gases
Calibration & Functional | Verify auto-calibration cycle
Calibration & Functional | Check drift limits compliance
Calibration & Functional | Verify alarm/fault signals to DCS
Calibration & Functional | Perform response time test
Calibration & Functional | Close punch list items
© Instrunexus ¦ www.instrunexus.com