## Control Valve
Pre‑Commissioning Checklist – Control Valve
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | Control Valve
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Documentation Verification | Verify tag vs. P&ID and instrument index
Documentation Verification | Check datasheet values vs. installed valve
Documentation Verification | Review vendor GA drawing and orientation
Documentation Verification | Confirm actuator sizing calculation available
Documentation Verification | Check calibration and test certificates
Documentation Verification | Verify PED/ASME certificates for pressure parts
Mechanical Installation | Check valve body orientation vs. flow arrow
Mechanical Installation | Verify gasket condition and correct torque
Mechanical Installation | Check flange alignment and bolt tightening
Mechanical Installation | Confirm valve installed in correct location
Mechanical Installation | Inspect stem packing condition
Mechanical Installation | Check body drains/vents installed
Mechanical Installation | Confirm support/clamps for actuator weight
Mechanical Installation | Verify accessibility for maintenance
Actuator & Positioner | Verify actuator air supply pressure rating
Actuator & Positioner | Check tubing connections for leaks
Actuator & Positioner | Inspect air filter regulator installation
Actuator & Positioner | Confirm handwheel/override works
Actuator & Positioner | Check actuator travel limit adjustment
Actuator & Positioner | Verify positioner calibration 0–100%
Actuator & Positioner | Check stroke time against datasheet
Actuator & Positioner | Inspect feedback linkage connection
Electrical & Wiring | Check solenoid wiring per diagram
Electrical & Wiring | Verify grounding of actuator accessories
Electrical & Wiring | Inspect junction box tagging and sealing
Electrical & Wiring | Confirm power supply rating
Electrical & Wiring | Check position feedback transmitter wiring
Loop & Signal | Perform loop check 4–20 mA to DCS
Loop & Signal | Verify valve position feedback trend
Loop & Signal | Check split range configuration (if any)
Loop & Signal | Simulate demand signal and verify travel
Loop & Signal | Check travel vs. DCS indication
Loop & Signal | Verify tight shutoff at 0% demand
Functional & Safety | Check stroking time open/close
Functional & Safety | Verify fail action (fail open/closed)
Functional & Safety | Check seat leakage vs. standard (API 598/ISO 5208)
Functional & Safety | Verify safety interlock signals
Functional & Safety | Confirm tagging and labeling
Functional & Safety | Perform final punch list clearance
© Instrunexus ¦ www.instrunexus.com