## DCS Cabinet
DCS Cabinet Commissioning Checklist
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | DCS Cabinet
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Pre-Requisites | Verify pre-commissioning checklist signed off
Pre-Requisites | Confirm GA drawings, wiring diagrams, I/O list available
Pre-Requisites | Check FAT/SAT reports closed
Pre-Requisites | Verify punch list clearance
Power-Up / Energization | Energize cabinet and check PSU status LEDs
Power-Up / Energization | Verify redundant power supply switchover
Power-Up / Energization | Check UPS backup duration
Power-Up / Energization | Confirm controller boot-up diagnostics
Functional Testing | Verify I/O modules recognized by system
Functional Testing | Check controller redundancy switchover
Functional Testing | Simulate DI and confirm DCS response
Functional Testing | Simulate AI and verify scaling in DCS
Functional Testing | Perform DO/DO relay test
Functional Testing | Check communication modules active
Functional Testing | Verify HMI/DCS interface
Functional Testing | Perform loop checks for representative signals
Integration & Interlocks | Verify historian logging
Integration & Interlocks | Check alarms and events recorded
Integration & Interlocks | Confirm Cause & Effect implementation
Integration & Interlocks | Verify permissives and interlocks tested
Safety & Compliance | Inspect hazardous area glands and seals
Safety & Compliance | Verify cabinet earthing continuity
Safety & Compliance | Check ambient temperature inside cabinet
Safety & Compliance | Confirm as-built documentation updated
Safety & Compliance | Close punch list items
© Instrunexus ¦ www.instrunexus.com