## DCS Cabinet
Pre‑Commissioning Checklist – DCS Cabinet
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | DCS Cabinet
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Documentation Verification | Verify cabinet tag vs. GA drawing
Documentation Verification | Check wiring diagrams availability
Documentation Verification | Review I/O list vs. modules installed
Documentation Verification | Confirm power load calculation
Documentation Verification | Check grounding layout drawing
Documentation Verification | Review vendor FAT reports
Mechanical Installation | Verify cabinet orientation and mounting
Mechanical Installation | Check cabinet anchoring and leveling
Mechanical Installation | Inspect cabinet doors, locks, hinges
Mechanical Installation | Confirm ventilation fans/filters installed
Mechanical Installation | Check earthing bar installed
Mechanical Installation | Verify cable entry plates installed
Mechanical Installation | Confirm nameplate and tagging
Power Supply | Verify redundant power supply installation
Power Supply | Check UPS input and output
Power Supply | Inspect DC distribution wiring
Power Supply | Verify fuses/circuit breakers ratings
Power Supply | Check switchover between redundant PSUs
Power Supply | Confirm PSU health LEDs indication
I/O Modules | Verify module types vs. I/O list
I/O Modules | Check spare slots populated with blanks
I/O Modules | Inspect module LEDs status
I/O Modules | Confirm hot-swap capability
I/O Modules | Check redundancy for controllers
I/O Modules | Verify firmware version of modules
Communication / Networking | Verify Ethernet switches installed
Communication / Networking | Check fiber optic terminations
Communication / Networking | Confirm redundancy in comms
Communication / Networking | Verify patch panel connections
Communication / Networking | Check cabinet LAN labeling
Internal Wiring | Verify termination torque
Internal Wiring | Check segregation of signal/power cables
Internal Wiring | Inspect ferrule numbers vs. drawings
Internal Wiring | Confirm shielding grounding at one end
Internal Wiring | Check fuses and terminals labeled
External Field Wiring | Verify marshalling terminals labeled
External Field Wiring | Check field cable continuity
External Field Wiring | Perform insulation resistance tests
External Field Wiring | Confirm gland plate installation
External Field Wiring | Check spare terminals identified
System / Loop Checks | Perform power-up of cabinet
System / Loop Checks | Check controller boot sequence
System / Loop Checks | Verify I/O channel diagnostics
System / Loop Checks | Simulate input and verify DCS response
System / Loop Checks | Perform loop check field to DCS
System / Loop Checks | Verify alarm annunciation in DCS
Functional & Safety | Confirm cabinet earthing continuity
Functional & Safety | Check ambient temperature inside cabinet
Functional & Safety | Verify access/clearance for maintenance
Functional & Safety | Perform final punch list clearance
© Instrunexus ¦ www.instrunexus.com