## Displacer Level Tran
Displacer Level Transmitter Commissioning Checklist
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | Displacer Level Transmitter
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Pre-Requisites | Verify pre-commissioning checklist signed off
Pre-Requisites | Confirm displacer datasheet and calibration certificate
Pre-Requisites | Check displacer cage hydrotested and drained
Pre-Requisites | Verify accessibility for maintenance
Pre-Requisites | Close punch list items
Power-Up / Energization | Energize transmitter and verify diagnostics
Power-Up / Energization | Check redundant PSU functionality
Power-Up / Energization | Confirm communication with DCS/PLC
Functional Testing | Fill cage with liquid and verify level indication
Functional Testing | Simulate HH and LL alarms
Functional Testing | Check specific gravity setting
Functional Testing | Verify span and zero calibration
Functional Testing | Confirm cage isolation valves operable
Integration & Interlocks | Verify trip logic from level input
Integration & Interlocks | Confirm permissives linked to displacer output
Integration & Interlocks | Check historian logging
Safety & Compliance | Verify hazardous area compliance
Safety & Compliance | Check NE43 fail-safe
Safety & Compliance | Confirm proof test procedure executed
Safety & Compliance | Close punch list items
© Instrunexus ¦ www.instrunexus.com