## ESD Valve
Pre‑Commissioning Checklist – Emergency Shutdown Valve
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | ESD Valve
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Documentation Verification | Verify tag vs. P&ID and instrument index
Documentation Verification | Check datasheet values vs. installed valve
Documentation Verification | Review vendor GA drawing and actuator type
Documentation Verification | Confirm SIL certificate and proof test interval
Documentation Verification | Check certificates for fire-safe design (API 607/ISO 10497)
Mechanical Installation | Check valve orientation and flow arrow
Mechanical Installation | Verify flange alignment and gasket installation
Mechanical Installation | Confirm torque per vendor recommendation
Mechanical Installation | Check accessibility for actuator and solenoid
Mechanical Installation | Inspect actuator mount and supports
Mechanical Installation | Verify painting/coating condition
Actuator/Pneumatics | Check actuator supply pressure
Actuator/Pneumatics | Verify quick exhaust valve installed
Actuator/Pneumatics | Confirm accumulator/bladder pre-charge pressure
Actuator/Pneumatics | Inspect tubing connections for leaks
Actuator/Pneumatics | Verify handwheel/override operation
Actuator/Pneumatics | Check actuator stroke time
Actuator/Pneumatics | Confirm fail-safe action
Electrical & Solenoids | Verify solenoid coil voltage vs. datasheet
Electrical & Solenoids | Check wiring diagram compliance
Electrical & Solenoids | Inspect junction box tagging
Electrical & Solenoids | Verify grounding and continuity
Electrical & Solenoids | Check limit switch wiring
Electrical & Solenoids | Confirm ESD solenoid energize/de-energize action
Functional & Safety | Check valve closes fully on ESD signal
Functional & Safety | Measure closure time vs. datasheet
Functional & Safety | Perform partial stroke test
Functional & Safety | Verify leakage class vs. datasheet
Functional & Safety | Check SIL loop logic in DCS
Functional & Safety | Perform proof test procedure
Functional & Safety | Verify compliance with safety case
© Instrunexus ¦ www.instrunexus.com