## F&G Cabinet
F&G Cabinet Commissioning Checklist
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | F&G Cabinet
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Pre-Requisites | Verify pre-commissioning checklist signed off
Pre-Requisites | Confirm cause & effect and wiring diagrams available
Pre-Requisites | Check FAT/SAT reports closed
Pre-Requisites | Verify punch list clearance
Power-Up / Energization | Energize F&G cabinet
Power-Up / Energization | Check PSU redundancy operation
Power-Up / Energization | Verify UPS backup capacity
Power-Up / Energization | Confirm controller diagnostics
Functional Testing | Simulate smoke detector input
Functional Testing | Simulate flame detector input
Functional Testing | Simulate gas detector input
Functional Testing | Verify output to sirens and beacons
Functional Testing | Check deluge valve actuation
Functional Testing | Verify alarm/event logging
Functional Testing | Perform Cause & Effect matrix testing
Integration & Interlocks | Verify shutdown signals to IPS/DCS
Integration & Interlocks | Check historian logging
Integration & Interlocks | Confirm permissives tested
Integration & Interlocks | Verify redundancy in communication
Safety & Compliance | Inspect hazardous area glands/seals
Safety & Compliance | Confirm earthing continuity
Safety & Compliance | Check ambient ventilation system
Safety & Compliance | Verify proof test procedure executed
Safety & Compliance | Close punch list items
© Instrunexus ¦ www.instrunexus.com