## F&G Cabinet
Pre‑Commissioning Checklist – F&G Cabinet
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | F&G Cabinet
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Documentation Verification | Verify cabinet tag vs. GA drawing
Documentation Verification | Check cause & effect matrix available
Documentation Verification | Review wiring diagrams
Documentation Verification | Confirm I/O list vs. modules installed
Documentation Verification | Check FAT reports
Mechanical Installation | Verify cabinet mounting orientation
Mechanical Installation | Inspect door locks, gaskets
Mechanical Installation | Check ventilation fans installed
Mechanical Installation | Confirm earthing bar installed
Mechanical Installation | Verify nameplate/tagging
Power Supply | Verify redundant PSUs installed
Power Supply | Check UPS switchover operation
Power Supply | Confirm DC distribution wiring
Power Supply | Inspect fuses/circuit breakers
Power Supply | Verify PSU health LEDs
Detector Inputs | Verify smoke detector input modules
Detector Inputs | Check flame detector input modules
Detector Inputs | Confirm gas detector input modules
Detector Inputs | Inspect diagnostic LEDs
Detector Inputs | Check spare input modules
Outputs / Actuators | Verify siren/beacon outputs
Outputs / Actuators | Check deluge valve outputs
Outputs / Actuators | Confirm ESD trip signals
Outputs / Actuators | Inspect output relays
Outputs / Actuators | Check redundancy in outputs
Internal Wiring | Verify labeling of terminals
Internal Wiring | Check segregation of signal/power
Internal Wiring | Inspect ferrule numbering
Internal Wiring | Confirm torque of terminals
Internal Wiring | Verify shield terminations
External Wiring | Check field cable tagging
External Wiring | Verify insulation resistance test
External Wiring | Confirm gland plates sealed
External Wiring | Check spare terminals marked
System Tests | Power-up cabinet and check status
System Tests | Verify communication with DCS
System Tests | Simulate smoke detector alarm
System Tests | Simulate flame detector alarm
System Tests | Simulate gas detector alarm
System Tests | Verify sirens and beacons activation
System Tests | Confirm deluge valve operation
Functional & Safety | Verify cause & effect logic works
Functional & Safety | Check event/alarm logging
Functional & Safety | Confirm SIL classification (if required)
Functional & Safety | Perform proof test procedure
Functional & Safety | Close punch list items
© Instrunexus ¦ www.instrunexus.com