## Flame Detector
Flame Detector Commissioning Checklist
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | Flame Detector
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Pre-Requisites | Verify pre-commissioning checklist signed off
Pre-Requisites | Confirm datasheet and hazardous area certificates
Pre-Requisites | Check test torch available and calibrated
Pre-Requisites | Verify installation angle and field of view per layout
Power-Up / Energization | Energize detector and check diagnostics
Power-Up / Energization | Verify redundant PSU switchover
Power-Up / Energization | Check communication with F&G cabinet
Functional Testing | Perform live flame test using test torch
Functional Testing | Verify alarm at F&G cabinet
Functional Testing | Check trip signal to ESD system
Functional Testing | Confirm response time vs datasheet
Functional Testing | Verify alarm reset function
Functional Testing | Check fault simulation response
Integration & Interlocks | Verify Cause & Effect alarm/trip logic
Integration & Interlocks | Confirm alarm logging in historian
Integration & Interlocks | Check redundancy of detectors in same zone
Safety & Compliance | Inspect hazardous area glands/seals
Safety & Compliance | Confirm NE43 fail-safe behavior
Safety & Compliance | Close punch items
© Instrunexus ¦ www.instrunexus.com