## Flame Detector
Pre‑Commissioning Checklist – Flame Detector
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | Flame Detector
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Documentation Verification | Verify tag vs. P&ID and F&G layout
Documentation Verification | Check datasheet vs. installed detector
Documentation Verification | Review hazardous area certification
Documentation Verification | Confirm calibration/test certificates
Documentation Verification | Check vendor GA drawing
Mechanical Installation | Verify field of view matches layout
Mechanical Installation | Check mounting height vs. datasheet
Mechanical Installation | Confirm correct angle/orientation
Mechanical Installation | Inspect sunshade/rain hood installed
Mechanical Installation | Check vibration resistance
Mechanical Installation | Verify accessibility for testing
Electrical & Cabling | Verify wiring vs. diagram
Electrical & Cabling | Check cable gland sealing
Electrical & Cabling | Confirm grounding continuity
Electrical & Cabling | Inspect junction box tagging
Electrical & Cabling | Check polarity of supply wiring
Electrical & Cabling | Confirm shielding continuity
Calibration / Functional Testing | Verify self-test diagnostics
Calibration / Functional Testing | Perform flame test with IR/UV torch
Calibration / Functional Testing | Check detector response time
Calibration / Functional Testing | Verify alarm and trip thresholds
Calibration / Functional Testing | Confirm event recorded in F&G system
Integration / Safety | Check alarm annunciation at DCS/F&G
Integration / Safety | Verify trip signal to ESD system
Integration / Safety | Confirm redundancy as per SIL design
Integration / Safety | Perform system walkdown
Integration / Safety | Close punch items
© Instrunexus ¦ www.instrunexus.com