## Flow Inst PreComm
Pre‑Commissioning Checklist – Flow Instruments
Project Name:
Location:
Instrument Tag:
Instrument Type:
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Documentation Verification | Verify instrument tag against P&ID and instrument index
Documentation Verification | Check calibration certificate availability and validity
Documentation Verification | Verify data sheet parameters against installed instrument
Documentation Verification | Check vendor drawings for correct installation orientation
Documentation Verification | Confirm material certificates for wetted parts if applicable
Documentation Verification | Verify ITP/QA records and FAT reports available
Mechanical Installation | Verify instrument mounting as per orientation requirement
Mechanical Installation | Check straight run requirements upstream/downstream are met
Mechanical Installation | Check impulse line connection, slope, and routing
Mechanical Installation | Ensure proper supports and clamps for impulse lines
Mechanical Installation | Verify impulse line flushing and cleanliness
Mechanical Installation | Check manifold valves installation and accessibility
Mechanical Installation | Ensure correct orifice plate orientation and centering (DP)
Mechanical Installation | Verify gasket alignment and correct tightening torque
Mechanical Installation | Confirm drain/vent points are installed and reachable
Electrical Installation | Check electrical connections as per wiring diagram
Electrical Installation | Verify power supply availability and polarity
Electrical Installation | Check grounding and cable shielding continuity
Electrical Installation | Inspect cable gland sealing and termination quality
Electrical Installation | Verify junction box connections, ferrules, and tagging
Electrical Installation | Check insulation resistance test results recorded
Electrical Installation | Confirm surge protection/earthing for ultrasonic/mag meters
Loop and Signal Checks | Perform loop check from transmitter to DCS/PLC
Loop and Signal Checks | Verify 4–20 mA/HART/Fieldbus signal communication
Loop and Signal Checks | Check range and zero/span calibration settings
Loop and Signal Checks | Simulate flow signal and verify DCS/PLC response
Loop and Signal Checks | Confirm low‑flow cut‑off/alarm configuration if applicable
Loop and Signal Checks | Check totalizer/pulse output scaling (if used)
Loop and Signal Checks | Verify signal stability and noise levels on trend
Functional and Safety Checks | Verify process isolation valves operation
Functional and Safety Checks | Leak test impulse lines and process connections
Functional and Safety Checks | Confirm heat tracing and insulation if required
Functional and Safety Checks | Ensure hazardous‑area compliance (Ex‑proof/IS)
Functional and Safety Checks | Verify transmitter fail‑safe settings (NAMUR NE43)
Functional and Safety Checks | Confirm proper tagging and labeling of all instruments
Functional and Safety Checks | Perform final walkdown and close punch items
© Instrunexus ¦ www.instrunexus.com