## Guided Wave Radar Le
Pre‑Commissioning Checklist – Guided Wave Radar Level Transmitter
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | Guided Wave Radar Level Transmitter
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Documentation Verification | Verify tag vs. P&ID and instrument index
Documentation Verification | Check datasheet vs. installed transmitter
Documentation Verification | Review calibration certificate
Documentation Verification | Confirm probe length vs. datasheet
Documentation Verification | Check hazardous area certificate
Mechanical Installation | Verify probe immersion depth
Mechanical Installation | Check nozzle orientation
Mechanical Installation | Confirm probe straightness
Mechanical Installation | Inspect process connection gasket
Mechanical Installation | Verify mounting flange torque
Mechanical Installation | Ensure probe free of obstructions
Mechanical Installation | Check reference reflector installation
Electrical & Cabling | Check wiring vs. diagram
Electrical & Cabling | Verify grounding/shielding
Electrical & Cabling | Inspect junction box tagging
Electrical & Cabling | Confirm gland sealing
Calibration / Configuration | Enter tank geometry
Calibration / Configuration | Perform false echo mapping
Calibration / Configuration | Verify range setting vs. datasheet
Calibration / Configuration | Check dielectric constant setting
Calibration / Configuration | Confirm alarm settings
Functional & Safety Checks | Perform loop check to DCS
Functional & Safety Checks | Verify trend response
Functional & Safety Checks | Check diagnostics via HART
Functional & Safety Checks | Confirm fail-safe configuration
Functional & Safety Checks | Close punch list items
© Instrunexus ¦ www.instrunexus.com