## IPS Cabinet
IPS Cabinet Commissioning Checklist
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | IPS Cabinet
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Pre-Requisites | Verify pre-commissioning checklist signed off
Pre-Requisites | Confirm logic diagrams and SIL certificates available
Pre-Requisites | Check FAT reports closed
Pre-Requisites | Verify punch list clearance
Power-Up / Energization | Energize IPS cabinet
Power-Up / Energization | Check PSU redundancy operation
Power-Up / Energization | Verify UPS backup capacity
Power-Up / Energization | Confirm logic solver diagnostics
Functional Testing | Simulate DI and confirm IPS response
Functional Testing | Simulate AI and verify scaling
Functional Testing | Perform DO test to solenoids
Functional Testing | Check 1oo2, 2oo3 voting logic operation
Functional Testing | Verify watchdog timer functionality
Functional Testing | Test redundancy of processors
Functional Testing | Verify Cause & Effect trips
Integration & Interlocks | Check shutdown signals to DCS
Integration & Interlocks | Verify permissives tested
Integration & Interlocks | Confirm alarm/event logging
Integration & Interlocks | Verify SIL loop testing
Safety & Compliance | Verify hazardous area compliance
Safety & Compliance | Confirm cabinet earthing continuity
Safety & Compliance | Check segregation of safety signals
Safety & Compliance | Confirm proof test documentation
Safety & Compliance | Close punch list items
© Instrunexus ¦ www.instrunexus.com