## IPS Cabinet
Pre‑Commissioning Checklist – IPS Cabinet
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | IPS Cabinet
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Documentation Verification | Verify cabinet tag vs. GA drawing
Documentation Verification | Check SIL certificate availability
Documentation Verification | Review logic diagrams
Documentation Verification | Confirm I/O list vs. modules installed
Documentation Verification | Check power load calculation
Documentation Verification | Review FAT reports
Mechanical Installation | Verify cabinet mounting and anchoring
Mechanical Installation | Inspect door locks, seals
Mechanical Installation | Confirm fire protection inside room
Mechanical Installation | Check earthing bar installed
Mechanical Installation | Inspect ventilation system
Power Supply | Verify redundant PSUs installed
Power Supply | Check UPS switchover operation
Power Supply | Inspect fuses/breakers ratings
Power Supply | Confirm PSU health LEDs
Power Supply | Verify 24V DC distribution
I/O Modules & Safety Cards | Verify I/O module type vs. logic
I/O Modules & Safety Cards | Check 1oo2, 2oo3 voting cards installed
I/O Modules & Safety Cards | Confirm spare capacity installed
I/O Modules & Safety Cards | Check redundancy of processors
I/O Modules & Safety Cards | Verify firmware versions
Relays & Solenoids Interface | Check safety relays installed
Relays & Solenoids Interface | Verify solenoid drivers functioning
Relays & Solenoids Interface | Inspect interposing relays
Relays & Solenoids Interface | Check redundancy of critical relays
Internal Wiring | Verify terminal labeling
Internal Wiring | Check ferrule numbers vs. drawings
Internal Wiring | Inspect segregation of SIS signals
Internal Wiring | Confirm shielding grounding
Internal Wiring | Check torque of terminals
External Field Wiring | Verify marshalling panel connections
External Field Wiring | Check field wiring tagging
External Field Wiring | Perform insulation resistance tests
External Field Wiring | Confirm spare terminals identified
External Field Wiring | Check gland plate sealing
System Diagnostics | Verify cabinet power-up sequence
System Diagnostics | Check diagnostic LEDs
System Diagnostics | Confirm watchdog timer operation
System Diagnostics | Verify processor redundancy
System Diagnostics | Check communication redundancy
Functional Safety | Perform logic solver self-test
Functional Safety | Verify cause & effect implementation
Functional Safety | Check trip initiation signals
Functional Safety | Perform proof test procedure
Functional Safety | Confirm SIL loop compliance
Functional Safety | Close punch items
© Instrunexus ¦ www.instrunexus.com