## Motor Operated Valve
Pre‑Commissioning Checklist – Motor Operated Valve
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | Motor Operated Valve
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Documentation Verification | Verify tag vs. P&ID and instrument index
Documentation Verification | Check datasheet values vs. installed valve
Documentation Verification | Review vendor GA drawing and motor type
Documentation Verification | Confirm torque/torque switch settings available
Documentation Verification | Check FAT reports and certificates
Mechanical Installation | Check valve body orientation vs. flow arrow
Mechanical Installation | Verify flange alignment and gasket installation
Mechanical Installation | Inspect gearbox and couplings
Mechanical Installation | Check supports for actuator weight
Mechanical Installation | Verify lubrication condition
Motor & Gearbox | Check motor insulation resistance test report
Motor & Gearbox | Verify torque switch setting
Motor & Gearbox | Check limit switch setting
Motor & Gearbox | Verify manual override works
Motor & Gearbox | Inspect motor nameplate vs. datasheet
Electrical & Control Wiring | Check motor wiring vs. SLD
Electrical & Control Wiring | Verify interlock wiring
Electrical & Control Wiring | Inspect junction box tagging
Electrical & Control Wiring | Confirm breaker/fuse rating
Electrical & Control Wiring | Check cable terminations
Limit Switches & Feedback | Check open/close limit switches function
Limit Switches & Feedback | Verify remote feedback signal in DCS
Limit Switches & Feedback | Check intermediate position indication
Limit Switches & Feedback | Verify fail-safe settings (if UPS backed)
Functional & Safety | Operate valve locally open/close
Functional & Safety | Operate valve remotely open/close
Functional & Safety | Verify stroke time
Functional & Safety | Check torque trip settings
Functional & Safety | Confirm interlock logic in DCS
Functional & Safety | Perform emergency operation test
© Instrunexus ¦ www.instrunexus.com