## Orifice-DP Flowmeter
Orifice/DP Flowmeter Commissioning Checklist
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | Orifice-DP Flowmeter
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Pre-Requisites | Verify pre-commissioning checklist signed off
Pre-Requisites | Confirm calibration certificate available
Pre-Requisites | Ensure as-built P&ID and datasheet updated
Pre-Requisites | Check work permit / LOTO in place
Pre-Requisites | Verify punch list items closed
Power-Up / Energization | Energize DP transmitter and check LEDs
Power-Up / Energization | Verify redundant 24V DC power supply operation
Power-Up / Energization | Check UPS switchover functionality
Power-Up / Energization | Verify cabinet PSU status in marshalling panel
Functional Testing | Simulate DP signal with calibrator
Functional Testing | Verify flow indication in DCS
Functional Testing | Check span and zero live with process fluid
Functional Testing | Confirm totalizer operation in DCS
Functional Testing | Verify alarm settings for low/high flow
Functional Testing | Check low-flow cut-off logic in DCS
Functional Testing | Perform leak test of impulse lines under process pressure
Functional Testing | Check manifold valve operability under live conditions
Functional Testing | Verify isolation valves open/close operation
Functional Testing | Confirm purge system operational (if installed)
Integration & Interlocks | Verify Cause & Effect trip on low flow
Integration & Interlocks | Check shutdown permissives for pumps/compressors
Integration & Interlocks | Confirm flow indication used in control loop
Integration & Interlocks | Verify historian logging and trending
Integration & Interlocks | Check redundancy in DP transmitters (if dual)
Safety & Compliance | Inspect hazardous area glands/seals live
Safety & Compliance | Verify NAMUR NE43 fail-safe response
Safety & Compliance | Check SIL loop test record updated
Safety & Compliance | Confirm alarms logged in event historian
Safety & Compliance | Verify as-built drawings signed
© Instrunexus ¦ www.instrunexus.com