## Pressure Transmitter
Pre‑Commissioning Checklist – Pressure Transmitter
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | Pressure Transmitter
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Documentation Verification | Verify tag vs. P&ID and instrument index
Documentation Verification | Check datasheet vs. installed transmitter
Documentation Verification | Review calibration certificates
Documentation Verification | Verify hazardous area certification
Documentation Verification | Confirm vendor drawings
Mechanical Installation | Check tapping point orientation
Mechanical Installation | Verify flange alignment and gasket
Mechanical Installation | Confirm siphon/snubbers installed (if required)
Mechanical Installation | Inspect isolation valve operation
Mechanical Installation | Check impulse line cleanliness
Mechanical Installation | Confirm mounting orientation
Mechanical Installation | Check support brackets installed
Electrical & Cabling | Verify power supply connection
Electrical & Cabling | Check polarity and grounding
Electrical & Cabling | Inspect junction box tagging
Electrical & Cabling | Confirm cable gland sealing
Electrical & Cabling | Check shielding continuity
Calibration / Configuration | Set zero and span vs. datasheet
Calibration / Configuration | Simulate pressure signal to DCS
Calibration / Configuration | Verify alarm settings (HH, LL)
Calibration / Configuration | Confirm NE43 fail-safe configuration
Functional & Safety | Perform loop check to DCS
Functional & Safety | Verify trend stability
Functional & Safety | Check leak test on connections
Functional & Safety | Confirm hazardous area compliance
Functional & Safety | Close punch list items
© Instrunexus ¦ www.instrunexus.com