## Resistance Temperatu
Pre‑Commissioning Checklist – RTD
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | Resistance Temperature Detector
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Documentation Verification | Verify tag vs. P&ID and instrument index
Documentation Verification | Check datasheet vs. installed RTD
Documentation Verification | Review calibration certificates
Documentation Verification | Confirm thermowell drawing
Mechanical Installation | Verify insertion depth vs. datasheet
Mechanical Installation | Check thermowell orientation
Mechanical Installation | Inspect leak test results
Mechanical Installation | Confirm thermowell material certs
Mechanical Installation | Check accessibility for removal
Electrical & Cabling | Verify 3-wire/4-wire connection
Electrical & Cabling | Check polarity vs. diagram
Electrical & Cabling | Inspect junction box tagging
Electrical & Cabling | Confirm gland sealing
Electrical & Cabling | Check shielding continuity
Calibration / Configuration | Verify resistance vs. temperature table
Calibration / Configuration | Simulate RTD signal
Calibration / Configuration | Check transmitter scaling (if used)
Calibration / Configuration | Confirm alarm settings
Functional & Safety | Perform loop check
Functional & Safety | Verify DCS trend
Functional & Safety | Check response time
Functional & Safety | Confirm hazardous area compliance
Functional & Safety | Close punch items
© Instrunexus ¦ www.instrunexus.com