## Temperature Transmit
Temperature Transmitter Commissioning Checklist
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | Temperature Transmitter
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Pre-Requisites | Verify pre-commissioning checklist signed off
Pre-Requisites | Confirm datasheet, calibration, and software revision
Pre-Requisites | Check thermowell integrity
Power-Up / Energization | Energize TT and check diagnostics
Power-Up / Energization | Verify redundant PSU switchover
Power-Up / Energization | Confirm communication with DCS
Functional Testing | Simulate RTD/TC input signal
Functional Testing | Verify scaling matches datasheet
Functional Testing | Check alarm setpoints HH/LL
Functional Testing | Verify NE43 fail-safe signal
Functional Testing | Perform loop check to DCS
Integration & Interlocks | Confirm permissives implemented
Integration & Interlocks | Verify historian trending
Safety & Compliance | Verify hazardous area compliance
Safety & Compliance | Close punch items
© Instrunexus ¦ www.instrunexus.com