## Ultrasonic Flowmeter
Pre‑Commissioning Checklist – Ultrasonic Flowmeter
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | Ultrasonic Flowmeter
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Documentation Verification | Verify instrument tag against P&ID and instrument index
Documentation Verification | Check calibration/test certificate
Documentation Verification | Verify velocity range vs. datasheet
Documentation Verification | Confirm serial numbers vs. certificates
Documentation Verification | Check vendor drawings for installation details
Mechanical Installation | Verify transducer alignment and spacing
Mechanical Installation | Confirm pipe internal condition (free of deposits/scale)
Mechanical Installation | Check straight run requirements as per datasheet
Mechanical Installation | Verify gasket/bolt installation for inline ultrasonic meters
Mechanical Installation | Ensure clamp-on transducers are installed with coupling gel
Mechanical Installation | Check sensor orientation (V-path, Z-path) as per vendor
Mechanical Installation | Verify pipe schedule and diameter entered correctly
Mechanical Installation | Confirm vibration levels acceptable
Electrical Installation | Check cabling between transducers and transmitter
Electrical Installation | Verify grounding/shielding
Electrical Installation | Check power supply and communication wiring
Electrical Installation | Inspect junction box tagging and sealing
Electrical Installation | Check hazardous area glands/ex-seals
Loop & Signal Checks | Perform loop check transmitter to DCS/PLC
Loop & Signal Checks | Verify velocity, volumetric flow, and diagnostics output
Loop & Signal Checks | Check signal strength and path diagnostics
Loop & Signal Checks | Simulate flow conditions and verify output
Loop & Signal Checks | Verify failover between multiple paths if applicable
Loop & Signal Checks | Check temperature input scaling (if used)
Functional & Safety Checks | Confirm hazardous area compliance
Functional & Safety Checks | Verify alarm/fault relay outputs
Functional & Safety Checks | Check fail-safe behavior on signal loss
Functional & Safety Checks | Verify diagnostic/alarm limits in transmitter
Functional & Safety Checks | Perform final punch list clearance
© Instrunexus ¦ www.instrunexus.com