## Visual Alarm
Visual Alarm Commissioning Checklist
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | Visual Alarm
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Pre-Requisites | Verify pre-commissioning checklist signed off
Pre-Requisites | Confirm datasheet and hazardous area certs
Pre-Requisites | Check flash rate specification
Pre-Requisites | Verify installation visibility per layout
Power-Up / Energization | Energize beacon and check diagnostics
Power-Up / Energization | Verify redundant PSU switchover
Power-Up / Energization | Check communication with F&G cabinet
Functional Testing | Activate beacon locally
Functional Testing | Activate beacon from F&G cabinet
Functional Testing | Verify flash rate vs datasheet
Functional Testing | Check visibility at design distance
Functional Testing | Confirm alarm reset function
Integration & Interlocks | Verify Cause & Effect activation
Integration & Interlocks | Confirm historian logging
Integration & Interlocks | Check redundancy of alarms in same zone
Safety & Compliance | Verify hazardous area compliance
Safety & Compliance | Confirm fail-safe behavior
Safety & Compliance | Close punch items
© Instrunexus ¦ www.instrunexus.com