## pH & Conductivity An
Pre‑Commissioning Checklist – pH & Conductivity Analyzer
Project Name:
Location:
Instrument Tag:
Instrument Type: |  | pH & Conductivity Analyzer
Prepared By:
Checked By:
Approved By:
Date: |  | 2025-09-01
Activity Category | Checklist Item | Completed | Remarks
Documentation Verification | Verify tag vs. P&ID and instrument index
Documentation Verification | Check datasheet vs. installed analyzer
Documentation Verification | Review calibration certificates
Documentation Verification | Verify vendor drawing for installation
Documentation Verification | Check material certificates for probe
Documentation Verification | Confirm spare probe availability
Sensor/Probe Inspection | Inspect pH electrode condition
Sensor/Probe Inspection | Check conductivity probe cell constant
Sensor/Probe Inspection | Verify probe immersion depth
Sensor/Probe Inspection | Confirm correct flow cell installation
Sensor/Probe Inspection | Check junction box connections
Sensor/Probe Inspection | Verify temperature compensation probe
Mechanical Installation | Verify sample point orientation
Mechanical Installation | Check isolation valves operable
Mechanical Installation | Inspect sample line flushing system
Mechanical Installation | Confirm bypass arrangement installed
Mechanical Installation | Check accessibility for probe removal
Electrical & Cabling | Check cable gland sealing
Electrical & Cabling | Verify shielding/grounding
Electrical & Cabling | Confirm transmitter wiring vs. diagram
Electrical & Cabling | Inspect power supply rating
Electrical & Cabling | Check junction box tagging
Calibration & Standardization | Perform buffer solution calibration
Calibration & Standardization | Check slope and offset values
Calibration & Standardization | Verify conductivity calibration with standard solution
Calibration & Standardization | Confirm temperature compensation response
Calibration & Standardization | Document calibration results
Functional & Safety Checks | Perform loop check 4–20 mA/HART
Functional & Safety Checks | Verify DCS/PLC trend response
Functional & Safety Checks | Check alarm settings for high/low pH
Functional & Safety Checks | Check alarm settings for conductivity range
Functional & Safety Checks | Confirm hazardous area compliance
Functional & Safety Checks | Close punch items
© Instrunexus ¦ www.instrunexus.com